LAIQ Stage 1 Budget
Oil & Gas Inspection Copilot

Investor submission version

# 1. Executive Summary

• Stage 1 product: Oil & Gas Inspection Copilot.

• Delivery window: 6 months.

• Core engineering headcount ramps to 4 by Month 6.

• Full report generation is included by the end of Month 6.

• Estimated project budget: about SGD 250k, including modest contingency.

This plan is based on a tablet-first field product and a lean infrastructure model aligned to the current project scope.

# 2. Stage 1 Product Scope

Included deliverables

• Inspection setup, scope, task board, and draft handling.

• Shell UT, roof UT, shell nozzle UT, roof nozzle UT.

• Inline findings with photos and evidence linking.

• Shell precise mapping.

• Bottom via MFL import / reference workflow.

• Review flow, export package, and full report generation by Month 6.

• Basic backend, authentication, storage, and pilot deployment readiness.

# 3. Recommended Team

| Role | Headcount | Start month | Responsibility | Delivery focus |
| --- | --- | --- | --- | --- |
| Technical lead / senior full-stack | 1 | Month 1 | Architecture and delivery leadership | System design, report pipeline, critical path |
| Product engineer | 1 | Month 1 | Field workflow and UX | Capture screens, offline flow, measurement UX |
| Backend / platform engineer | 1 | Month 2 | Platform and report services | API, persistence, files, report generation |
| QA / automation engineer | 1 | Month 4 | Quality assurance and hardening | Automation, device QA, pilot readiness |

Product management and design are assumed to be covered internally. The only non-core delivery support budgeted here is part-time inspection subject matter expert (SME) / reviewer support.

Core engineering ramp

| Month | Core engineers active | Active roles |
| --- | --- | --- |
| 1 | 2 | Technical lead, Product engineer |
| 2 | 3 | Technical lead, Product engineer, Backend / platform engineer |
| 3 | 3 | Technical lead, Product engineer, Backend / platform engineer |
| 4 | 4 | Technical lead, Product engineer, Backend / platform engineer, QA / automation engineer |
| 5 | 4 | Technical lead, Product engineer, Backend / platform engineer, QA / automation engineer |
| 6 | 4 | Technical lead, Product engineer, Backend / platform engineer, QA / automation engineer |

# 4. Six-Month Delivery Timeline

Stage 1 outcome at Month 6: the product must support end-to-end field capture and full report generation from captured inspection data.

| Month | Core engineers active | Focus | Output |
| --- | --- | --- | --- |
| 1 | 2 | Foundations | Data model, app shell, auth, storage, inspection lifecycle, report schema |
| 2 | 3 | Core capture workflow | Setup, scope, task board, shell UT, shell findings, shell mapping |
| 3 | 3 | Remaining capture flows | Roof UT, nozzle UT, MFL import, review flow, evidence management |
| 4 | 4 | Report generation engine | Template structure, table rendering, evidence linking, report assembly logic |
| 5 | 4 | Full report generation + hardening | End-to-end report output, offline behavior, QA automation, performance |
| 6 | 4 | Pilot readiness | Bug fixing, deployment, field feedback, report tuning, generated report acceptance |

# 5. Budget Summary

| Item | Budget |
| --- | --- |
| Estimated operating budget | SGD 237.5k |
| Contingency reserve | SGD 12.5k |
| Estimated total project budget | SGD 250.0k |
| Cloud services | SGD 1.5k / month |
| Coding / LLM API | SGD 1.5k / month |
| Full report generation | Included by Month 6 |

# 6. Budget Breakdown

| Budget line | Budget | Description |
| --- | --- | --- |
| Engineering team (ramp to 4 over 6 months) | SGD 204.5k | Core product build across app, backend, reporting, and QA |
| Part-time inspection SME / reviewer | SGD 10.0k | Inspection-domain validation and report review |
| Cloud service budget | SGD 9.0k | SGD 1.5k per month from Month 1 |
| Coding / LLM API budget | SGD 9.0k | SGD 1.5k per month from Month 1 |
| Devices, software, and test tooling | SGD 5.0k | Rugged-device testing, software, QA setup |
| Contingency | SGD 12.5k | Lean delivery buffer and pilot-readiness reserve |

# 7. Monthly Expense Schedule

All figures below are shown in SGD '000 and reflect estimated monthly operating burn. Cloud and coding / LLM API costs are budgeted from Month 1 onward. Contingency is shown separately.

| Month | Engineering | Inspection SME | Cloud | Coding / LLM API | Devices / Tools | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 22.0 | 1.0 | 1.5 | 1.5 | 2.0 | 28.0 |
| 2 | 32.0 | 1.0 | 1.5 | 1.5 | 1.5 | 37.5 |
| 3 | 32.0 | 1.5 | 1.5 | 1.5 | 0.5 | 37.0 |
| 4 | 39.5 | 2.0 | 1.5 | 1.5 | 0.5 | 45.0 |
| 5 | 39.5 | 2.0 | 1.5 | 1.5 | 0.5 | 45.0 |
| 6 | 39.5 | 2.5 | 1.5 | 1.5 | 0.0 | 45.0 |
| Total | 204.5 | 10.0 | 9.0 | 9.0 | 5.0 | 237.5 |

Engineering burn is based on blended fully-loaded monthly costs for a Singapore / regional team: technical lead at about SGD 13k/month, product engineer at about SGD 9k/month, backend / platform engineer at about SGD 10k/month, and QA / automation engineer at about SGD 7.5k/month.

Contingency reserve: SGD 12.5k, held outside monthly operating burn and used only for delivery risk, pilot surprises, or final report-output hardening.

# 8. Delivery Outcome at Month 6

• Field capture workflow operational for Stage 1 oil & gas tank inspection scope.

• Shell, roof, nozzle, and MFL workflows complete.

• Evidence-linked inspection record available for review and export.

• Full report generation available from captured inspection data.

• Pilot-ready product release prepared for customer deployment.

# 9. Budget Position

The Stage 1 budget is designed around a progressive staffing ramp to 4 engineers by Month 6 and includes full report generation within the 6-month delivery window.

For investor submission and planning purposes, LAIQ should use an estimated Stage 1 project budget of about SGD 250k.